## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Fetch the latest AI news articles so we can analyze them. | MUST HAVE | NewsAPI | Udit Ray | 3- Completed
S1 | S1 | US-002 | Classifying the sentiment of each AI news headline using TextBlob so that we can understand its tone. | MUST HAVE | TextBlob | Udit Ray | 3- Completed
S2 | S2 | US-003 | Cleaning the text for analysis so that LLM can process it correctly. | MUST HAVE | No Dependency | Udit Ray | 3- Completed
S2 | S2 | US-004 | Classifying AI news sentiment using Gemini LLM for more accurate sentiment scoring. | SHOULD HAVE | GeminiAPI | Udit Ray | 3- Completed
S2 | S2 | US-005 | Sending slack alerts for negative news headlines so that stakeholders are notified in real-time. | SHOULD HAVE | Slack | Udit Ray | 3- Completed
S3 | S3 | US-006 | Fetching AI news for multiple keywords and create a clean sentiment dataset for forecasting. | MUST HAVE | NewsAPI | Udit Ray | 3- Completed
S3 | S3 | US-007 | Aggregating daily sentiment scores from news so that anomalies can be detected. | SHOULD HAVE | No Dependency | Udit Ray | 3- Completed
S3 | S3 | US-008 | Detecting anomalies in daily sentiment and get slack alerts for unusual patterns. | SHOULD HAVE | No Dependency | Udit Ray | 3- Completed
S3 | S3 | US-009 | Forecasting sentiment for the next 5 days using Chronos so that we can anticipate trends. | MUST HAVE | Chronos Model | Udit Ray | 3- Completed
S3 | S3 | US-010 | Detecting keyword surges on the latest news so that trending topics are highlighted and alerted. | MUST HAVE | No Dependency | Udit Ray | 3- Completed
S3 | S3 | US-011 | Visualizing actual vs forecasted sentiment and mark anomalies for better insights. | SHOULD HAVE | Chronos Model | Udit Ray | 3- Completed
S4 | S4 | US-012 | Build a Streamlit dashboard to fetch, display, and analyze AI news with sentiment visualization. | MUST HAVE | Streamlit | Udit Ray | 3- Completed
S4 | S4 | US-013 | Enable filters in the dashboard to select keywords and date ranges for customized analysis. | MUST HAVE | Streamlit | Udit Ray | 3- Completed
S4 | S4 | US-014 | Display sentiment trends, keyword benchmarks, and alerts interactively in the dashboard. | MUST HAVE | Streamlit | Udit Ray | 3- Completed
S4 | S4 | US-015 | Forecasting future sentiment scores using Chronos for selected keywords. | MUST HAVE | Streamlit | Udit Ray | 3- Completed
S4 | S4 | US-016 | Forecast future sentiment and detect anomalies directly in the dashboard for decision support. | MUST HAVE | Streamlit | Udit Ray | 3- Completed
S4 | S4 | US-017 | Provide downloadable CSVs of news, sentiment, and forecast for reporting purposes. | MUST HAVE | Streamlit | Udit Ray | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 65 | 34 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T01 | Setup NewsAPI & environment | 2025-08-19 | 2025-08-19 | Udit Ray | Coding | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T02 | Fetch initial AI news | 2025-08-21 | 2025-08-22 | Udit Ray | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T03 | Implement sentiment analysis | 2025-08-23 | 2025-08-23 | Udit Ray | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 LLM Integration & Slack Alerts
US-003 | T04 | Clean & preprocess news text | 2025-09-01 | 2025-09-01 | Udit Ray | Coding | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T05 | Configure Gemini API | 2025-09-02 | 2025-09-03 | Udit Ray | Coding | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T06 | Integrate LLM sentiment analysis | 2025-09-04 | 2025-09-06 | Udit Ray | Coding | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T07 | Send Slack alerts on negative sentiment | 2025-09-07 | 2025-09-08 | Udit Ray | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T08 | Test & validate alerts | 2025-09-09 | 2025-09-09 | Udit Ray | Testing | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 Forecast & Anomaly Detection
US-007 | T09 | Aggregate daily sentiment scores | 2025-09-11 | 2025-09-12 | Udit Ray | Coding | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T10 | Implement Chronos forecasting | 2025-09-13 | 2025-09-15 | Udit Ray | Coding | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T11 | Plot forecast & anomalies | 2025-09-16 | 2025-09-17 | Udit Ray | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T12 | Validate forecasting accuracy | 2025-09-18 | 2025-09-19 | Udit Ray | Testing | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 Streamlit Dashboard & UI
US-012 | T13 | Setup Streamlit dashboard | 2025-09-21 | 2025-09-21 | Udit Ray | Coding | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T14 | Integrate news fetching, sentiment, keyword benchmarks and alerts | 2025-09-22 | 2025-09-24 | Udit Ray | Testing | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T15 | Implement forecast & anomaly plots | 2025-09-25 | 2025-09-27 | Udit Ray | Testing | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T16 | Add CSV download & filters | 2025-09-28 | 2025-09-29 | Udit Ray | Testing | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T17 | Test dashboard & finalize | 2025-09-30 | 2025-10-01 | Udit Ray | Deployment | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Faced issue connecting to NewsAPI (invalid key error) | Generated a new API key and tested connection successfully
Sprint 1 | Day 2 | Some news articles contained broken Unicode characters | Added text cleaning using ftfy and regex patterns
Sprint 1 | Day 3 | Sentiment analysis returned inaccurate results for neutral texts | Tuned polarity thresholds and tested with sample data
Sprint 2 | Day 1 | LLM integration caused timeout errors | Optimized API call limit and added retry logic
Sprint 2 | Day 3 | Slack alert messages not formatted properly | Fixed JSON message structure and tested delivery
Sprint 3 | Day 2 | Forecast model (Chronos) not loading properly | Installed missing dependencies and reloaded pipeline
Sprint 3 | Day 3 | Forecast graph not showing correctly | Adjusted matplotlib plot rendering.
Sprint 4 | Day 1 | Dashboard layout misaligned in wide screen | Used Streamlit’s layout="wide" and adjusted column widths
Sprint 4 | Day 2 | File upload not accepting CSVs properly | Added .csv to accepted file types and tested upload
Sprint 4 | Day 3 | Forecast tab took too long to load | Cached resource loading using @st.cache_resource

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-19 | 2025-08-23 | Udit Ray | Started working on fetching AI-related news using NewsAPI | Stop delaying daily testing and commits | Continue improving data cleaning and preprocessing | Successfully fetched and cleaned news data from API
2 | Sprint 2 | 2025-09-01 | 2025-09-09 | Udit Ray | Started implementing sentiment analysis using TextBlob or GeminiAPI | Stop using unstructured output formats | Continue improving accuracy of sentiment results | Integrated TextBlob sentiment module and exported CSV
3 | Sprint 3 | 2025-09-11 | 2025-09-19 | Udit Ray | Started adding Chronos model for forecasting | Stop manual analysis using Excel | Continue model testing for better forecast | Added automated forecast and visualization of results
4 | Sprint 4 | 2025-09-21 | 2025-10-01 | Udit Ray | Started developing Streamlit dashboard | Stop focusing only on backend | Continue UI and functionality improvements | Built a Streamlit web app for interactive analysis